## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
S1 | TA creates applicant profiles | As a TA I want to create a personal applicant profile (name/ID/academic major/skills/contact info) So that I can register and apply for TA jobs | Must have | 1 | 1. The form contains all required fields (name, student ID, major, etc.); 2. Clear error prompt pops up when submitting null values; 3. Save the data to a local JSON file; 4. Saved files can be edited and saved again. | 3 | Core basic functions, relying on S11 (login) | week 3 | week 4
S2 | TA uploaded the resume | As a TA I want to upload my CV as a PDF/TXT file So that MO can view my personal background | Must have | 1 | 1. Only PDF/TXT format files are allowed; 2. Files larger than 5MB are rejected and prompted; 3. Display file name and timestamp after successful upload; | 2 | Dependency S1 (file creation), S11 (login) | week 3 | week 4
S3 | MO releases job vacancies | As a MO I want to post TA job info (job name/requirements/working hours/responsibilities) So that TAs can view and apply for suitable jobs | Must have | 1 | 1. The job posting form contains all required fields; 2. Save the job information to a CSV file and sort it in descending order by publication date; 3. MO can only edit/delete the positions they have posted; 4. Clearly display the application deadline to TA. | 3 | MO core operation, relying on S11 (login) | week 3 | week 4
S4 | TA views available positions | As a TA I want to view all available TA jobs (filter by major/skills) So that I can find jobs matching my ability | Must have | 1 | 1. Only display positions that have not expired; 2. Click on the job title to view complete details; 3. The job data is loaded correctly from the CSV file. | 2 | Dependent on S3 (job posting) and S11 (login) | week 3 | week 4
S5 | TA applies for a position | As a TA I want to submit an application for a selected TA job So that MO can review my application | Must have | 1 | 1.The "Apply" button is only visible to logged in TAs; 2. Apply for automatic association of TA files and resumes; 3. The same TA can only apply for the same position once; 4. Save the application data to a JSON file. | 2 | Dependent on S1, S2, S4, S11 | week 3 | week 4
S6 | TA view application status | As a TA I want to check the status of my job applications (pending/reviewed/accepted/rejected) So that I can know the result of my application | Must have | 2 | 1. Display all application records in descending order of application time; 2. Each application clearly displays the current status; 3. Display status update timestamp; 4. The status data is correctly loaded from the application JSON file. | 1 | Dependent on S5 (job application) and S11 (login) | week 5 | week 6
S7 | MO views job applicants | As a MO I want to view all applicants for the jobs I posted So that I can review and select suitable TAs | Must have | 2 | 1. Display all application records in descending order of application time; 2. Each application clearly displays the current status; 3. Display status update timestamp; 4. The status data is correctly loaded from the application JSON file. | 3 | Dependent on S3, S5, S11 | week 5 | week 6
S8 | MO updates application status | As a MO I want to update the application status (accept/reject/pending) So that TAs can know the review result | Must have | 2 | 1. The status selection is in the form of a drop-down box; 2. Real time synchronization to TA after status update; 3. Record MO ID and update timestamp; 4. Pop up the prompt "Update successful". | 2 | Dependent on S7 (view applicant), S11 (login) | week 5 | week 6
S9 | Admin views the overall workload of TA | As an Admin I want to view the overall workload of all hired TAs So that I can balance the TA working load | Should have | 3 | 1. Support sorting by TA ID/total duration; 2. The workload is automatically calculated and updated in real-time; 3. The data is presented in clear tabular form. | 5 | Admin basic functions, relying on S8 (MO hiring TA) and S11 | week 9 | week 10
S10 | AI assisted MO analysis of job matching with applicant skills | As a MO I want AI to analyze skill match between job requirements and applicants' profiles, and identify missing skills So that I can evaluate applicants objectively | Could have | 4 | 1. Calculate the matching percentage and display matching/missing skills; 2. Lack of skill labeling importance; 3. Support sorting candidates by matching degree; 4. the results can be exported as TXT. | 8 | AI core functions, relying on S3, S5, S11 | week 11 | week 12
S11 | System user registration and login | As a TA/MO/Admin I want to register (role selection) and log in So that I can access role-exclusive functions | Must have | 1 | 1. The registration page supports role selection; 2. The password must be ≥ 8 characters and contain both letters and numbers; 3. Unique username, duplicate registration prompt; 4. Login failed 3 times and locked for 5 minutes; 5. Encrypt and store credentials in TXT. | 5 | Pre dependencies for all functions | week 3 | week 4
S12 | Admin exports TA workload data | As an Admin I want to export workload data to CSV/TXT So that I can archive and analyze | Should have | 3 | 1. Support CSV/TXT format selection; 2. Export the file with TA ID/name/duration/timestamp; 3. Automatically save to the specified directory; | 3 | Dependent on S9 and S11 | week 9 | week 10
S13 | System data backup and recovery | As an Admin I want to back up/restore system data So that I can prevent data loss | Could have | 3 | 1. One click backup of all data files; 2. Isolate backup permissions by role; 3. Optional backup file recovery; 4. After the operation, a success/failure prompt will pop up. | 5 | System stability guarantee, relying on S11 | week 9 | week 10
S14 | AI assisted Admin balances TA workload | As an Admin I want AI to recommend workload adjustments So that I can balance TA workload more reasonably | Could have | 4 | 1. Calculate workload balance; 2. Generate specific adjustment suggestions; 3. Suggestions include adjustment criteria and matching degree; 4. Admin manually confirms adoption. | 8 | AI extension function, relying on S9, S10, S11 | week 11 | week 12
S15 | System pushes key event message notifications | As a TA/MO I want to receive system in-app notifications for key recruitment events So that I can grasp the recruitment progress in a timely manner | Want to have | 4 | 1.TA receives notifications for application status update, position expiration and withdrawal success 2.MO receives notifications for new applications 3.Support marking notifications as read/unread and clearing all read ones | 3 | User experience optimization, relying on S3, S5, S8 | week 11 | week 12
S16 | TA modifies unapproved work applications | As a TA I would like to withdraw the pending teaching assistant job application So that I can cancel incorrect or unexpected applications | Want to have | 4 | 1. Only support withdrawal of applications with "pending" status; 2. Pop up a double confirmation prompt before withdrawal; 3. Update application status to "withdrawn" and record withdrawal timestamp; | 2 | Application management function, relying on S5, S6, S11 | week 11 | week 12